## Slide 1
Purpose statement |  |  |  | 
In collaboration with ACC, design a rural unplanned, urgent care system that is responsive to rural communities’ needs and results in equity of both access and outcomes. |  |  |  | 
Te Tiriti o Waitangi statement |  |  |  | 
In partnership with IMPBs, improve experience and equity of access to unplanned, urgent care for all rural communities, with focus on improved health outcomes for rural Māori. |  |  |  | 
Problem definition – what problems does this workstream need to solve? |  | Objective – what will this workstream deliver? |  | 
Rural communities face inequitable access to unplanned, urgent care, especially during after hours. Distance, roading, climate change impacts, and seasonal population fluctuations cause clinical safety concerns for unplanned, urgent care in rural areas. Service viability is increasingly challenged in rural areas due to workforce shortages, unsustainable funding mechanisms and pressures in primary care. The current system and work conditions of PRIME personnel increase operational and clinical risk for both patients and providers. An outdated unplanned, urgent care system that is not effectively integrated into the wider primary and emergency care system and lacks the ability to address existing and longstanding concerns. |  | By working alongside IMPBs, the re-design will capture and weave iwi Māori aspirations to develop a more responsive and whānau-centred rural unplanned, urgent care system for Māori. Improve access to unplanned, urgent care for rural populations who face barriers including those that are unenrolled. An unplanned, urgent care system that is innovative and improves equity of access for all rural communities including Pacific Peoples, high deprivation, unenrolled patients, older people and people with disability and mental health needs. A well-considered and collaborative re-design process that utilises a relational commissioning approach for a truly integrated rural unplanned, urgent care system. Identify options to sustainably fund rural unplanned, urgent care whilst supporting workforce need and enhancing rural service viability. Implement an unplanned, urgent care system that supports the operational and clinical safety of providers and patients. |  | 
What clinical services need to be considered in order to deliver the purpose and objectives? |  |  |  | 
General practice and PRIME service Road and air ambulance, including communications and secondary triage EDs/A&Ms Aged care | Pharmacy After hours and urgent care services District nursing, midwifery and axillary services Unregulated workforce, including kaiawhina |  | Allied health Rural hospitals, retrieval services Telehealth including Ka Ora FENZ Palliative care | 
Key Stakeholders – who’s voices do we need to hear to expertly inform this work? |  | Dependencies |  | 
External stakeholders Rural and remote community members and wider community voice, iwi Māori PRIME patients, former and current PRIME providers Hato Hone St John, Wellington Free Ambulance and air ambulance providers, Patient Transfer Providers FENZ Police, Search & Rescue, Rescue Coordination Centre Mental Health Hauora Taiwhenua PHOs including those in rural areas with no current PRIME provision, General practices, GPNZ NZ Nursing Council, NZ College of Primary Care Nurses and Royal New Zealand College of General Practitioners, Royal New Zealand College of Urgent Care, Medical Council, Te Kaunihera Manapou, training institutions Telehealth providers, including Ka Ora and Whakarongorau; IT and mobile logistics Local government, Surf Lifesaving, Coastguard Aged residential care, Palliative care; Community Support Trusts Oranga Tamariki and MSD MoH and MPI Other Allied Health |  | Other Primary Care Development workstreams (capitation work, meso review, urgent care) TeleHealth Review Rural Hospital Sustainability Project |  | Internal stakeholders National Rural Health team Regional rural teams Ambulance Team Wider Living Well team and Commissioning teams Rural Clinical Health Network (currently under development) Iwi Māori Partnership Boards Hauora Māori Services Group (formerly Te Aka Whai Ora) Ministry of Health rural clinical lead and policy lead Mental health and addiction team Disability leads Hospital Specialist Services National Public Health Service
Programme Brief – Rural Unplanned, Urgent Care Re-design

## Slide 2
Purpose statement
In collaboration with ACC, design a rural unplanned, urgent care system that is responsive to rural communities’ needs and results in equity of both access and outcomes.
Approach to working with partners
Underpinning our relational commissioning approach, our re-design process will take an inclusive, collaborative and transparent approach with all partners. Therefore, we will: Work closely with ACC to agree upon project scope and to align related work, including national urgent care review Collaborate with Hato Hone St John as the existing administrators of PRIME to address longstanding issues and to build a better system Uphold te Tiriti o Waitangi by partnering with Iwi Māori Partnership Boards to capture and weave iwi Māori aspirations throughout the re-design Maintain effective and transparent communication with all partners involved in the re-design journey
FOR FEEDBACK - Draft Programme Brief – Rural Unplanned, Urgent Care Re-design
Deliverables | Milestones
Project establishment Generate ongoing sponsorship - alongside stakeholders, agree on engagement and partnership approach, including a comms plan Develop a project governance mechanism – identify and define a core working advisory group Develop a project consultation mechanism - alongside key stakeholders/NPC, review the ToR for NPC Develop a scoping and discussion document (including a high-level road map) Consultation process defined | Mid May 2024
Current state analysis Map the variation of access to unplanned, urgent care across the motu Map the variation of outcomes for rural communities, with respect to urgent, unplanned care Collate and describe the range of service viability challenges for PRIME providers | End of June 2024
Re-design the rural unplanned, urgent care system for rural communities (PLAN PHASE) Via the project governance mechanism – generate solutions to inform the re-design Via the project consultation mechanism – circulate and discuss potential solutions Articulate the cost of delivery equitable unplanned, urgent care to rural communities, linking to the road Ambulance Activity Resource Model (AARM) review Complete a final paper outlining the different options for the re-design of the rural unplanned, urgent care system | End of September 2024
Full circle commissioning approach determined (PLAN PHASE) Seek approval of the final options paper via the project consultation mechanism for endorsement of the proposed new system Continue procurement and contractual processes Identify ongoing monitoring mechanisms for the new system Follow appropriate budget bid processes Maintain clear communication with all relevant stakeholders throughout this process | End of October 2024 November 2024 – February 2025
Transition to a new system (IMPLEMENTATION PHASE) (note a separate, detailed project plan will follow, based on preferred and endorsed options) Develop an implementation plan with clearly articulated mechanisms to monitor and review the new system. This might include procurement and contracting processes. Clearly communicate with all stakeholders (both internal and external) the implementation plan Continuously monitor and review the new unplanned, urgent care system | Jan 25 - July 2025